## Verification_Plan
TIMER DV TEST PLAN & VERIFICATION RESULT
Project: Timer IP Verification ¦ Protocol: APB Bus ¦ Generated: 2026
ID | Item | Sub item 1 | Sub item 2 | Test sequence | Pass condition | Test Class | Plan Start | Plan End | Actual Start | Actual End | PIC | Status
PHẦN 1: REGISTER ACCESS (Kiểm thử truy cập thanh ghi)
1 | Register access | TCR | Reset value check | After system reset is released, perform read access to TCR (offset= 0). | Read value = 32'h0000_0100 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
2 | Register access | TCR | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | 1. read value = 32'h0 2. read value = 32'h3 3. read value = 32'h0000_0501 4. read value = 32'h0000_0502 5. read value = 32'h0000_0502 | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
3 | Register access | TCR | Special access for div_val | 1. Write wdata[11:8] = 8 2. Write data[11:8] = 9 3. Write data[11:8] = 7 | 1. Can write to div_val, readback = 8 2. Can not write to div_val, div_val = 8 3. Can write to div_val, readback = 7 | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
4 | Register access | TDR0 | Reset value check | After system reset is released, perform read access to TDR0 (offset= 4). | Read value = 32'h0000_0000 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
5 | Register access | TDR0 | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | read value same as write value | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
6 | Register access | TDR1 | Reset value check | After system reset is released, perform read access to TDR1 (offset= 8). | Read value = 32'h0000_0000 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
7 | Register access | TDR1 | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | read value same as write value | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
8 | Register access | TCMP0 | Reset value check | After system reset is released, perform read access to TCMP0 (offset= 0xC). | Read value = 32'hFFFF_FFFF | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
9 | Register access | TCMP0 | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | read value same as write value | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
10 | Register access | TCMP1 | Reset value check | After system reset is released, perform read access to TCMP1 (offset= 0x10). | Read value = 32'hFFFF_FFFF | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
11 | Register access | TCMP1 | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | read value same as write value | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
12 | Register access | TIER | Reset value check | After system reset is released, perform read access to TIER (offset= 0x14). | Read value = 32'h0000_0000 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
13 | Register access | TIER | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | 1. read value = 32'h0 2. read value = 32'h1 3. read value = 32'h0000_0001 4. read value = 32'h0000_0000 5. read value = 32'h0000_0000 | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
14 | Register access | TISR | Reset value check | After system reset is released, perform read access to TISR (offset= 0x18). | Read value = 32'h0000_0000 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
15 | Register access | TISR | R/W access | 1. Clear interrupt by writing 1 to TISR 2. Read TISR to check it is 0 3. Write 0000_0000 & read back and compare 4. Write FFFF_FFFF & readback & compare 5. Write 5555_5555 & readback & compare 6. Write AAAA_AAAA & readback & compare 7. Write 5AA5_A55A & readback & compare | Write is not effect, read is always 0 | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
16 | Register access | THCSR | Reset value check | After system reset is released, perform read access to THCSR (offset= 0x1C). | Read value = 32'h0000_0000 | reg_init_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
17 | Register access | ` | R/W access | 1. Write 0000_0000 & read back and compare 2. Write FFFF_FFFF & readback & compare 3. Write 5555_5555 & readback & compare 4. Write AAAA_AAAA & readback & compare 5. Write 5AA5_A55A & readback & compare | 1. read value = 32'h0 2. read value = 32'h1 3. read value = 32'h0000_0001 4. read value = 32'h0000_0000 5. read value = 32'h0000_0000 | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
18 | Register access | Reserved registers | R/W access | - R/W 0xFFFF_FFFF to last address 0x4000_1FFC - R/W 0xFFFF_FFFF to first reserved address 0x4000_0020 | Write is not effect, read is always 0 | reg_reserved_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
19 | Register access | One-hot check |  | Write different value to all registers. After finish all, readback and compare | Read is same as expected value | reg_1hot_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
PHẦN 2: COUNTER (Kiểm thử hoạt động đếm bộ đếm chính)
20 | Counter | Counting behavior |  | Check counting at boundary of TDR0 is correct - Set TDR0 = 0xffff_ff00 - Set timer_en = 1 - Wait 256 cycle - Read TDR0 & TDR1 | - TDR1 is 1 - TDR0 is counting from the beginning. | cnt_counting_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
21 | Counter | Counting behavior |  | - Set TDR0 = 0xffff_ff00 - Set TDR1 = 0xffff_ffff - Set timer_en = 1 - Wait 256 cycle - Read TDR0 & TDR1 | - TDR1 is 0 - TDR0 is counting from the beginning. | cnt_counting_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
22 | Counter | Counter's value can be read from TDR0/TDR1 | Check counting at boundary of TDR0/1 | - Set TDR0 = 0xffff_ff00 - Set TDR1 = 0xffff_ffff - Set timer_en = 1 - Wait 256 cycle - Read TDR0 & TDR1 | - TDR1 is 0 - TDR0 is counting from the beginning. | cnt_counting_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
23 | Counter | Update TDR0/TDR1 when timer is working |  | - Set timer_en = 1, counter counts from 0 - Wait 256 cycle - Read counter and check it is counting normally - Set TDR1 = 0x0 - Set TDR0 = 0xffff_ff00 - Wait 256 cycle and read the counter | TDR1 is 1, TDR0 is counting from the beginning normally | cnt_counting_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
24 | Counter | Timer is disabled and resumed | When timer_en changed from 1->0. Counter does not count | - Setting for counter counts normally - Set timer_en = 0 | Counter does not count |  | TBD | TBD | TBD | TBD | Timer_DV | PASSED
25 | Counter | Timer is disabled and resumed | After timer_en changed from 1->0->1, counter works normally. When timer_en changes from 1 -> 0, hardware automatically resets TDR0 and TDR1 to 32'h0. No manual write is required | - Setting for counter to count normally - Set timer_en = 0 - Clear the TDR0/1 to 0 - Change the div_en/div_val - Set timer_en = 1 - Check the period when counter resume | The counting period must be correct for all mode | cnt_control_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
26 | Counter | Counter continue counting | When interrupt occurs | - Setting for interrupt occurs - Read TDR0/1 | Counter continues counting normally | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
27 | Counter | Counter continue counting | When overflow | - Setting for overflow occurs - Read TDR0/1 | Counter continues counting normally | cnt_counting_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
PHẦN 3: COUNTER CONTROL (Bộ chia tần số Prescaler)
28 | Counter control | default mode | div_en = 0 | - Set timer_en = 1 - Set div_en = 0 | Count same as system clock freq | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
29 | Counter control | control mode | div_en = 1, div_val = 0 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 0 | Count same as system clock freq | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
30 | Counter control | control mode | div_en = 1, div_val = 1 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 1 | Count freq = count/2 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
31 | Counter control | control mode | div_en = 1, div_val = 2 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 2 | Count freq = count/4 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
32 | Counter control | control mode | div_en = 1, div_val = 3 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 3 | Count freq = count/8 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
33 | Counter control | control mode | div_en = 1, div_val = 4 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 4 | Count freq = count/16 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
34 | Counter control | control mode | div_en = 1, div_val = 5 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 5 | Count freq = count/32 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
35 | Counter control | control mode | div_en = 1, div_val = 6 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 6 | Count freq = count/64 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
36 | Counter control | control mode | div_en = 1, div_val = 7 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 7 | Count freq = count/128 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
37 | Counter control | control mode | div_en = 1, div_val = 8 | - Set timer_en = 1 - Set div_en = 1 - Set div_val = 8 | Count freq = count/256 | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
38 | Counter control | Set div_val but does not set div_en | div_en = 0, div_val = 2 | - Set div_val = 2 - Set timer_en = 1 | Timer counts with system clock | cnt_ctrl_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
PHẦN 4: APB PROTOCOL (Kiểm thử giao thức APB)
39 | APB | Normal APB |  | Issue write then read to TDR0 | Read data is correct | apb_protocol_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
40 | APB | Wrong protocol | Psel does not assert, only Penable | - Issue wrong APB write - Then read normally | Data of register is not changed | apb_protocol_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
41 | APB | Wrong protocol | Penable does not assert, only Psel | - Issue wrong APB write - Then read normally | Data of register is not changed | apb_protocol_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
42 | APB | Pready |  | - Issue one transaction and check pready - 1-Cycle Wait State: tim_pready must be 0 in the first cycle of access and transition to 1 in the second cycle (1-cycle delay) [21, 28, 38]. | Pready is always 1 |  | TBD | TBD | TBD | TBD | Timer_DV | PASSED
43 | APB | Pslverr |  | Slave Error: tim_pslverr must be asserted High (1) whenever prohibited access occurs [28, 30, 38]. | Pslverr is always 0 |  | TBD | TBD | TBD | TBD | Timer_DV | PASSED
44 | APB | Multiple access | WW-RR | - Issue a multiple access to timer - Write continuously to TDR0/1 - Read continuously to TDR0/1 | Read data is correct | apb_multiple_access | TBD | TBD | TBD | TBD | Timer_DV | PASSED
45 | APB | Multiple access | WRWR | - Issue a multiple access to timer - Write and read TDR0 continuously - Write and read TDR1 continuously | Read data is correct | apb_multiple_access | TBD | TBD | TBD | TBD | Timer_DV | PASSED
46 | APB | Not aligned access |  | - Issue un-aligned access to timer - Example: write 0x1 0x2 0x3 then read the whole register | Register data is not changed | apb_unaligned_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
PHẦN 5: RESET & INTERRUPT (Kiểm thử Reset và tạo ngắt)
47 | Reset | Register |  | After reset, initial value is correct - Set timer to work normally - Assert reset - Check initial value of all register | Initial value must be correct | reg_rw_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
48 | Reset | Timer |  | After reset, timer can work normally - Set timer to work normally - Wait until interrupt asserts - Assert reset - Setting TCMP0/1, enable interrupt - Set timer_en = 1 | - When reset occurs, interrupt is cleared. - Check that interrupt can be asserted normally after reset | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
49 | Interrupt | interrupt pending | Set condition | - Set CMP = 0xff - Set timer_en = 1 - Wait 256 cycle and read TISR.int_st | - interrupt output is not asserted - TISR.int_st = 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
50 | Interrupt | interrupt pending | Clear condition | - Set CMP = 0xff - Set timer_en = 1 - Wait 256 cycle and read TISR.int_st - Write 0 to TISR.int_st and read back - Write 1 to TISR.int_st and read back | - interrupt output is not asserted - Write 0 to TISR.int_st, it remains 1 - Write 1 to TISR.int_st, it is cleared to 0 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
51 | Interrupt | interrupt pending | Manual condition | - Write TDR0/1 = 0xffff_ffff - Read TISR.int_st | - interrupt output is not asserted - TISR.int_st = 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
52 | Interrupt | interrupt enable | Set condition | - Set CMP = 0xff - Set TIER.int_en = 1 - Set timer_en = 1 - Wait 256 cycle and read TISR.int_st | - interrupt output is asserted - TISR.int_st = 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
53 | Interrupt | interrupt enable | Clear condition | - Set CMP = 0xff - Set TIER.int_en = 1 - Set timer_en = 1 - Wait 256 cycle and read TISR.int_st - Write 0 to TISR.int_st and read back - Write 1 to TISR.int_st and read back | - interrupt output is not asserted after clear - Write 0 to TISR.int_st, it remains 1 - Write 1 to TISR.int_st, it is cleared to 0 - interrupt output is cleared to 0 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
54 | Interrupt | interrupt enable | Manual condition | - Write TDR0/1 = 0xffff_ffff - Set TIER.int_en = 1 - Read TISR.int_st | - interrupt output is asserted - TISR.int_st = 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
55 | Interrupt | interrupt enable | Mask condition | - Set CMP = 0xff - Set TIER.int_en = 1 - Set timer_en = 1 - Wait 256 cycle and read TISR.int_st - set TIER.int_en = 0, check interrupt output and read TISR.int_st | - interrupt output is negated, - TISR.int_st still keeps 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
56 | Interrupt | Once asserted, interrupt must be kept |  | - Setting to assert the interrupt - Set timer_en = 0 - Check interrupt output and TISR.int_st | - Interrupt keeps High - int_st keeps 1 | interrupt_chk | TBD | TBD | TBD | TBD | Timer_DV | PASSED
PHẦN 6: BYTE ACCESS (Kiểm thử truy cập từng Byte - reg_byte_access)
57 | Byte access | TCR | Byte 0 write | Write 32'h0000_0003 with pstrb = 4'b0001 to 0x00 | div_en and timer_en update to 2'b11; div_val remains default 4'b0001 | reg_byte_access
58 | Byte access | TCR | Byte 1 write | While timer_en=0, write 32'h0000_0400 with pstrb = 4'b0010 to 0x00 | div_val updates to 4'b0100; timer_en and div_en stay 0 | reg_byte_access
59 | Byte access | TCMP0 | Individual byte writes | Write bytes 8'hAA, 8'hBB, 8'hCC, 8'hDD sequentially using pstrb = 4'b0001, 4'b0010, 4'b0100, 4'b1000 to 0x0C | TCMP0 reads back 32'hDDCCBBAA | reg_byte_access
60 | Byte access | TCMP1 | Individual byte writes | Write bytes 8'h11, 8'h22, 8'h33, 8'h44 sequentially using pstrb = 4'b0001, 4'b0010, 4'b0100, 4'b1000 to 0x10 | TCMP1 reads back 32'h44332211 | reg_byte_access
61 | Byte access | TDR0 / TDR1 | Partial byte strobe write | Write with pstrb = 4'b0011 to TDR0 (0x04) and pstrb = 4'b1100 to TDR1 (0x08) | Only targeted byte lanes update; non-strobed bytes preserve their existing values | reg_byte_access
PHẦN 7: ERROR HANDLING (Kiểm thử phản hồi lỗi APB - apb_pslverr_chk)
62 | APB Error | TCR | Prohibited div_val | Write div_val = 4'b1001 (value > 8) to TCR with pstrb[1]=1 | 1. tim_pslverr asserts High 2. div_val is not modified | apb_pslverr_chk
63 | APB Error | TCR | Change div_val while running | 1. Set timer_en = 1<br>2. Attempt to write a new div_val (4'b0010) to TCR | 1. tim_pslverr asserts High 2. div_val is not modified | apb_pslverr_chk
64 | APB Error | TCR | Change div_en while running | 1. Set timer_en = 1<br>2. Attempt to change div_en from 0 -> 1 | 1. tim_pslverr asserts High 2. div_en is not modified | apb_pslverr_chk
PHẦN 8: DEBUG HALT MODE (Kiểm thử chế độ tạm dừng Debug - cnt_halt_chk)
65 | Debug Halt | Normal Halt | Enter Halt mode | 1. Set dbg_mode = 1<br>2. Write THCSR.halt_req = 1 (0x1C) | 1. THCSR.halt_ack reads 1 ¦ 2. Counter freezes and stops counting | cnt_halt_chk
66 | Debug Halt | Normal Halt | Exit Halt mode | While dbg_mode = 1, write THCSR.halt_req = 0 | 1. THCSR.halt_ack returns to 0 ¦ 2. Counter resumes counting | cnt_halt_chk
67 | Debug Halt | Non-debug mode | halt_req when dbg_mode = 0 | 1. Set dbg_mode = 0<br>2. Write THCSR.halt_req = 1 | 1. THCSR.halt_ack remains 0 ¦ 2. Counter does not halt (continues counting) | cnt_halt_chk
68 | Debug Halt | Period preservation | Preserve counting tick phase | Set div_val = 2 (div-by-4). Halt for 2 clock cycles, then unhalt | The sub-cycle prescaler phase is preserved; tick period remains accurate | cnt_halt_chk
PHẦN 9: ADVANCED INTERRUPT (Ưu tiên xóa ngắt)
69 | Interrupt | Priority | Clearance vs Assertion | Perform a write of 1 to TISR.int_st at the exact same cycle count == tcmp occurs | Clear condition takes highest priority; TISR.int_st becomes 0 | interrupt_chk
70